## Sheet1
Internationalization
Bootstrap CSS+JS integration
Linting Review | Done | Built in to Angular CLI, run independently local, automatic on build
Access to JIRA | Done
Access to Skype | Done
Access to old app | Done | normal user in test
Access to old app code | Done
Access to mail on phone
Access to syncplicity (if needed)
Team Viewer for screen sharing
Angular Documentation Review | In Prcoess | it's gonna take atleast couple of more days
Developer story
Create initial,empty, barebones angular LevelUp app |  | Allows build/release pipeline work to start parallel and with smallest challenge
Integration with JIRA and code
Angular CLI Install and Review | Done
Visual Studio Code Installed & Plugins or App Reviewed | Done
Installed Node with NPM | Done
Spinner global or per component
base path definition for Angular | Done
Angular, CSS Animations | Almost Done
CKEditor (WYSYWIG) Angular Component replacement | Done | CkEditor Angular Component exists
Rating Stars strategy for Angular | Done | CSS3 + Angular can replace jQuery
Authentication with SSO strategy | Done | Web API will respond with a 302 to SSO
Authentication with Web API (cookie or header token?)
Web API (or other dependencies) URL across environment strategy
TeamCity setup | In Progress
Node.js and dependency installs on Team City server | In Progress
Browser Compatibility\Polyfills research and in read.me | Done
Choose an Angular UI Control library like ngx-bootstrap